## Sheet1
Task | Assignee | Estimation | Actual Effort
DAO Pattern | Nick | 8 hours | 10 hours
Autentication | Yixin | 3 hours | 4 hours
Unit Test | Yixin | 2 hours | 2 hours
Server/Client Comm | Haliunaa | 2 hours | 2 hours
Front End View | Haliunaa | 3 hours | 4 hours
Admin App | Sam | 4 hours | 5 hours
Integration + Debugging | Everyone | 6 hours | 9 hours
Total |  | 28 hours | 36 hours