## Sheet1
Task | Assignee | Estimation | Actual Effort
Admin App GUI | Nick | 5 hours | 6 hours
Test Coverage | Yixin | 3 hours | 4 hours
Server/Client GUI | Haliunaa | 6 hours | 7 hours
New Features | Wenxuan | 3 hours | 4 hours
Total |  | 28 hours | 36 hours